## Slide 1: Project Management, Lifecycle and Documentation
Project Management Unit #1

## Slide 2: What is a project?
A project is a complex, non-routine, one-time effort limited by time, budget, resources, and performance specification designed to meet specific needs.
  Examples include construction of a chemistry department building, holding a teacher development workshop, creating a new French dining experience
Projects generally have a particular set of characteristics in common
  A clearly stated objective
  A specific life span with beginning and end
  Multiple departments or people working together
  Usually something that has never been done before
  Must be done within specific time, cost and performance requirements

## Slide 3: Why manage a project?
Accomplish objectives of project within constraints
Balancing trade-offs between time, cost and performance
  These three constraints can be mutually exclusive
  An effective balance is necessary for project success
Anticipating, identifying and handling the unexpected
  Unexpected events will happen throughout a project (Murphy’s Law)
  Risk planning is an essential component to project management
Taking into account unique project features
  As project complexity increases coordination and risk also increase
  New technology development is usually associated with increased risk and complexity

## Slide 4: Project Team Structure
Dedicated project team structure
  Create independent team composed of specialists to focus exclusively on project
Project team management structure
  Maximum cohesion and focus provides fast response
  Resistance to “outsiders” and constrained staff expertise
  Appropriate for complex or organizations with many projects
You should establish a “Team Contract” to define your organization and interaction as a team

## Slide 5: Stages of Team Development
Forming: Get acquainted stage when ground rules, roles and interpersonal relations are established
Storming: Conflict stage when group control, decision making, group & project constraints are contested
Norming: Stage when close relationships develop and the group demonstrates cohesiveness
Performing: Established expectations of how to work together and the group begins channeling energy into achieving project goals
Adjourning: Attention is focused on completing the project and could include conflicting emotions

## Slide 6: Building a Project Team
Early on establish ground rules such as the following
  How will the project be planned?
  What will be the specific roles and responsibilities?
  How will progress be assessed and tracked?
  How will project changes be documented and instituted?
  How, when and where will meetings be scheduled and run?
Conduct project meetings that are regular, crisp, have a focused agenda and are time constrained
Establish a team identify and create a shared vision
Facilitate group decisions by identifying underlying problems, generating alternate solutions, fostering a consensus and following-up on solution implementation
Accepting, managing and encouraging functional conflict

## Slide 7: Project Team Pitfalls
Project teams and managers need to be aware of various pitfalls that can lead to poor decisions.
A team can become convinced that its decisions are infallible.
Fail to examine alternate solutions and problems that might arise from the current plan.
Stereotype outsiders negatively so that external concerns, issues or solutions remain unconsidered.
Opposition by a member to a particular direction or solution might be repressed by the team.

## Slide 8: The Project Phases
All projects complete roughly the same phases from inception to completion
OPERATION
DESIGN
PDR
DEVELOPMENT
CDR
FABRICATION
INTEGRATION
TESTING
FRR

## Slide 9: The Design Phase
Little to no hardware testing or prototyping
Define science goals and objectives
System level design (subject of a later lecture)
  System requirements derived from goals and objectives
  Identify major subsystems and interfaces
Concept hardware and software design
  Derived from system requirements and constraints
  Identify parts, costs & availability
Establish tasks, schedule, resource needs and plans for remaining phases of life-cycle
Develop preliminary risk assessment & management plan
Phase terminates with Preliminary Design Review (PDR)
“Paper” study of all issues to establish major concepts and plans

## Slide 10: The Development Phase - 1
Test concepts by prototyping
  Not building flight hardware
  Used to gain information necessary to refine or finalize a design
  Applies to structure, electronics, sensors and software
Finalize hardware & software design
  Complete system design
  Define interfaces and develop appropriate Interface Control Documents (ICD)
  Complete detailed design
Design
Prototype
Test
Complete Design
Detailed in-depth study when all design components are finalized

## Slide 11: The Development Phase - 2
Purchase long lead items (identified at PDR)
Finalize plans for pre-flight phases
  Fabrication, integration, calibration and testing
  Tasks, schedule, procedures, resource needs, costs
Update risk assessment & management plan
  Preliminary plan should already be in use for tracking and mitigating risks during development
Develop preliminary mission operations & data analysis plan
Phase terminates with Critical Design Review (CDR)

## Slide 12: The Fabrication Phase
Training
Integration
Thermal Test
QA / QC
Assembly
Order Parts
Inspect/Test
Parts procurement
  Test that parts satisfy flight requirements before assembly
Assemble hardware & software subsystems
  Training may be required for particular assemblies
  Fabricate component with qualified parts
  If part fails initial inspection and testing, return to assembly for rework / fixing
  If part fails thermal testing return to assembly for rework / fixing
Once complete move to integration
Implement construction of flight components

## Slide 13: The Integration Phase
Make sure all parts fit together, if not then rework
Make sure power system is delivering proper voltage and current
Connect electronics and sensors
Install software and run
Fix issues before proceeding to system testing
Fit Check
System Testing
Integrate
Fix
Test
Subassemblies are put together to make the final package

## Slide 14: The System Testing Phase
Payload flight certification
Functional Test
FRR
Fix
Calibration
Thermal Test
Pressure Test
Shock Test
Check Calibration
Integrated payload must first be fully functional
Calibration values are determined
  Sensors, ADC gain, timing
Payload must function correctly during thermal, pressure & shock testing
  If not, fix and begin again
  If OK, then validate calibrations
Test and test data must be documented
Proceed to Flight Readiness Review

## Slide 15: Mission Operations & Data Analysis (MO&DA)
Mission Operations plan includes the following
  Sequence of operations to prepare payload for vehicle integration
  Sequence of operations to prepare payload for launch
  Flight profile requirements
  Operations, commanding, contingencies during flight
  Recovery handling and operations
Data Analysis plan describes what happens to the flight data
  Flight data handling, processing and analysis sequence
  Specify data required from vehicle
Operate payload during flight & obtain science results

## Slide 16: The need for communication
Communication and documentation is key for a successful project
  “If it is not written down, it did not happen!” (ancient wise saying)
  “If you wrote it down, you agreed to do it!” (not as ancient wise saying)
Communication assures coordination of effort across stakeholders
  Agreement on how to proceed
  Tracking of progress
  Assure functioning interface between units
Written documentation provides the “glue” that stabilizes components and unifies the project
  Helps assure “end-to-end” thinking
  Show agreement on roles, tasks, schedule
  Provides proof of performance
Reports & presentations set precedent for acknowledgement of effort and / or discoveries

## Slide 17: The Project Reviews
There are at least three major reviews during a project
  Preliminary Design, Critical Design, Flight Readiness
  Also including a Pre-PDR and Pre-CDR to divide the reviews into more manageable sections
These reviews provide a check on project progress for all stakeholders
PDR, CDR and FRR are major project milestones
  Pre-PDR by end-January
  PDR by mid-February
  Pre-CDR by first part of March
  CDR by mid- to late- March
  FRR document by May & defense prior to launch
  Imposed duration on schedule is a risk to be managed
The team must prepare written documents and oral presentations for each review
Each review has a somewhat different objective and emphasis

## Slide 18: Preliminary Design Review (PDR)
The primary objective for the PDR is to review results from your design phase
At the end of the PDR you should have been able to show that you have “thought the problem through”
There will be two parts for the PDR
The Pre-PDR will focus on your mission goal, science background, objectives and requirements.
  Expect to do a Pre-PDR presentation
During the PDR you will build on the Pre-PDR
  Resolve issues identified in the Pre-PDR
  Add system design, concept instrument hardware & software design, risk analysis.
  There will be a PDR presentation AND document

## Slide 19: PDR Topics
The PDR should focus on the following topics:
  Goals and objectives  Pre-PDR
  Science background and requirements  Pre-PDR
  Preliminary System design
  Concept hardware & software design
  Tasks, schedule, resource needs, long-lead items  Pre-PDR
  Preliminary risk assessment & management plan
Use document template to guide your PDR write-up
  Similar document for CDR and FRR
PDR presentation should be about 30 minutes
  20 minutes of PowerPoint presentation
  10 minutes of questions from the review panel
  Cover content of PDR document

## Slide 20: Critical Design Review (CDR)
The primary objective of the CDR is to review the results from your development phase
Determines whether you are ready to begin building your payload
There will be two parts for the CDR
The Pre-CDR will focus on your PDR issues, prototype results, “proven” design, final system and interfaces.
  Expect to do a Pre-CDR presentation
During the CDR you will build on the Pre-CDR
  Resolve issues identified in the Pre-CDR
  There will be a CDR presentation AND document

## Slide 21: CDR Topics
CDR should follow the same format as the PDR
  Modify document template for CDR
  Same oral presentation format
CDR should emphasize the following topics:
  Resolving issues identified during the PDR  Pre-CDR
  Prototyping results and “proven” designs  Pre-CDR
  Completed system design and defined interfaces  Pre-CDR
  Finalize tasks, schedule, procedures and costs
  Updated risk assessment & management plan
  Preliminary MO & DA plan

## Slide 22: Flight Readiness Review (FRR)
Determine that all issues from CDR have been resolved
Document Experiment Readiness
  As-built configuration
  Environmental testing results
  Calibrations performed
Provide quantitative evidence that the payload:
  Meets requirements
  Is safe
  Will perform properly
Determine any impact on other payloads or the vehicle
Describe procedures for checkout, integration with the vehicle and mission operations
Identify outstanding issues that must be addressed prior to flight

## Slide 23: FRR Topics
FRR document follows same format at CDR
  Documentation of as-built configuration
  Prove that payload is safe, will perform properly and satisfies flight constraints
  Written FRR document sent to LA ACES Project two weeks before flight
Oral FRR presentation during the launch trip
The FRR will determine whether you are allowed to attach your payload to the flight vehicle!

## Slide 24: Post-Flight Science Report
During the launch trip you will be required to present a report on your preliminary science results
  PowerPoint presentation including science background, brief description of instrument, calibrations, analyzed data, science results and error analysis
You will have a full day following the flight to analyze your data and prepare your report
You will be provided with a time to altitude converter program for your flight
Recommend the following prior to the launch trip
  Have your presentation done except for the science results
  Have your calibrations complete and ready to apply
  Have your ground data handling and analysis software complete, tested and ready to go

## Slide 25: LSU 2020 Report Schedule
Pre-PDR
  Presentation January 28, 2020
PDR
  Presentation February 11, 2020
  Document Due February 14, 2020
Pre-CDR
  Presentation March 12, 2020
CDR
  Presentation March 19, 2020
  Document due March 31, 2020
System Testing
  Thermal / Vacuum Test April 17, 2020
FRR
  Document due April 28, 2020
All presentations start at 18:00 and all documents are due by 22:00 central time.

## Slide 26: LaACES 2020 Flight Schedule
Travel to NASA CSBF May 17, 2020
FRR Presentation May 18, 2020
Launch, Flight Ops May 19, 2020
Data Analysis May 20, 2020
Science Presentation May 21, 2020
Contingency Day May 22, 2020