## Slide 1: Building The Project Schedule

## Slide 2: The project scheduling process
Establishing a project schedule determines the time ordering of tasks, helps identify potential resource conflicts, and provides assurance about completion time.
A well defined schedule is also a very useful tool for monitoring progress.
Developing a project schedule includes the following steps:
  Establish the detailed WBS
  Determine the task dependence or precedence
  Identify time lags
  Roll-up time estimates from bottom level WBS
  Assign resources (i.e. people) to tasks & resolve conflicts
  Identify milestone dates
  Implement trade-off if schedule is not acceptable

## Slide 3: Factor affecting the schedule
Is the WBS complete?
  Undefined tasks or time lags can disrupt the planned schedule
How accurate is the work package time estimate?
  Uncertainty in the times for the lowest WBS level will propagate upward during roll-up
What is the level of task dependency?
  Dependent tasks can only be accomplished in sequence rather than in parallel. Thus, increasing the number of personnel will not necessarily reduce the time required to complete the tasks.
What is the availability of personnel resources?
  An individual can not focus on more than one task at a time. Thus, without sufficient personnel, tasks will need to be done sequentially.
What is the effectiveness of the personnel?
  Amount of time is a person or resource available for the project

## Slide 4: Essential schedule information
A complete WBS provides the first-order schedule organization
  All major tasks, subtasks, and milestone events should be identified
  The WBS units will usually already be in some kind of time ordering
Determine which tasks require the results from some previous task (i.e. task precedence)
  For example, you can not install a sensor until the sensor has been specified, ordered, and delivered
Determine which tasks can be accomplished in parallel
  For example, you can build multiple copies of the same design at the same time.
Identify milestone events and determine if any of these events require a fixed date
Identify and estimate the length of any time lags like shipping time, holidays, exam schedule, time off, etc.

## Slide 5: Begin “coding” the schedule
Usually done in software such as Microsoft Project, but can be done manually in Excel
Enter tasks from WBS into scheduling software
  Use software features to establish a “tree structure” relationship
  Lower-level tasks should be clearly associated with a higher-level task
  Don’t forget shipping time or other project-specific lags as “tasks” in the schedule
Enter time estimates for lowest lowest-level tasks and time lags
  These times should then be rolled up to the higher-level summary tasks
  Milestone events are indicated by having zero duration
Enter task and milestone predecessor information
Use software features to enter general time lags such as holidays, exam schedules, etc.

## Slide 6: Refinements to the schedule
Define the characteristics of your personnel resources and assign these resources to specific tasks (who is doing this work)
Take into account effects due to limited personnel availability (A person can only work on one task at a time)
Include lags to reflect the effectiveness of personnel
Improve the “parallelism” of your tasks
Check that the schedule is consistent with constraints (are you meeting deadlines)
Correct any schedule issues (May need to reassign personnel to assist tasks)

## Slide 7: Personnel availability
The schedule can be affected by the number of people with appropriate skills available to the project
Individuals can not work on multiple tasks at the same time
If two tasks that would normally be worked in parallel are assigned to the same individual, then these tasks must be made dependent and worked in sequence
This decision is made when assigning resources to tasks

## Slide 8: Personnel Effectiveness
Not everyone works at the same rate or has the same availability
Keep in mind that there is a difference between “time on task” and “calendar time”
Both available work time and work efficiency must be taken into account
If a task requires 40 hours of work …
  A normal 100% efficient worker will need 1 week of calendar time
  A worker who can only focus on a task for 10 hours per week will need four weeks of calendar time
Schedule software can automatically handle some of these effects

## Slide 9: Define personnel resources
Scheduling software should have some ability to define the characteristics of the project resources
  Shown is the Resource Information panel in Microsoft Project
These resources can then be assigned to particular tasks and the scheduling program will automatically take into account the resource characteristics
Characteristics of individuals include:
  Normal working time
  Personal absences
  Percent of work week devoted to project
  Calendar dates of availability

## Slide 10: Schedule tasks in parallel
Within personnel constraints, the more tasks you can schedule to run concurrently, the shorter your overall schedule will be.
Detailed WBS and task definitions may reveal opportunities for parallel effort.
  Fabrication of duplicates of the same design can be run in parallel
  Determine requirements early so development of different modules can run in parallel
Take advantage of “natural” time lags
  While parts for module A are being shipped, schedule work on module B

## Slide 11: Check for consistency
Make sure that your schedule is consistent with known constraints
Is there work scheduled when no one will be available?
Is the total work time shown in the schedule consistent with the total time personnel have committed to work?
Are the major milestones occurring on the expected or required dates?
Is the overall duration of the schedule as expected?

## Slide 12: Tracking your schedule
Once the initial schedule has been established, you should monitor progress
  If your schedule is on track, then you should show all tasks earlier than the current calendar date as being done
There are a few things you can do if you are running behind schedule
  Descope the project and eliminate tasks
  Increase the number of personnel working on the project
  Reassign tasks to more efficient or more available personnel
  Increase the number of hours personnel work on the project