Louisiana Space Grant

Guidance for No Cost Extension Requests

LaSPACE will no longer consider full-year No-Cost Extensions (NCEs). We may consider NCE requests for up to 6 months. We are getting more pressure from NASA to complete as much spending as possible within each program year. It is harder to justify NCEs for our subawarded projects. We need you to propose an NCE for only exactly how much additional time you need. If we deem that there are avoidable reasons for you needing an NCE, it may be rejected. Do your best to spend according to your proposed timeline. Reach out earlier rather than later if you hit early snags.

NCE’s for ongoing projects must be submitted to the LaSPACE program office no later than 60 days before the initial project end-date. All NCE requests must be submitted to laspace@lsu.edu, signed off on by your Office of Sponsored Programs administrators, and must include a progress report submitted by the PI which addresses all accomplishments made to-date on the project (including all publications, proposals, presentations, patents, etc), where the project is in relation to the originally proposed end date, reasons why the project has been delayed, and a proposed plan for completing the project. This progress report must also identify all participants on the project (students, post-docs, faculty, and staff).

A link to the online platform for progress report submission, as well as a document with detailed guidance for writing the report, are posted in the LaSPACE Document Center on our website.